## Sheet1
Gamified Learning Progress Tracker
Start-date | 2024-01-29
Task | Start-Date | End-Date | Duration
Planning | 2024-01-29 | 2024-02-01 | 1
Requirement | 2024-02-01 | 2024-02-08 | 1
Design | 2024-02-08 | 2024-02-28 | 3
Development | 2024-02-28 | 2024-03-24 | 4
Testing | 2024-03-24 | 2024-03-29 | 1
Documentation | 2024-01-29 | 2024-02-18 | 15
Deployment | -- | -- | --
Maintenance | -- | -- | --
Total weeks | -- | -- | 15
Formulas:
Start-Date = [End-Date, row above]
End-Date = [Start-Date]+3