## Sheet1
Gamified Learning Progress Tracker
Start-date | 2024-01-29
Task | Start-Date | End-Date | Duration
Planning | 2024-01-29 | 2024-02-01 | 3
Requirement | 2024-02-01 | 2024-02-08 | 7
Design | 2024-02-08 | 2024-02-28 | 20
Development | 2024-02-28 | 2024-03-24 | 25
Testing | 2024-03-24 | 2024-03-29 | 5
Documentation | 2024-01-29 | 2024-04-08 | 65
Deployment | -- | -- | --
Maintenance | -- | -- | --
Total days | -- | -- | 65
Formulas:
Start-Date = [End-Date, row above]
End-Date = [Start-Date]+3